## Scrum Board
Sprint | User Story | Task | Assignee | Status | Story Points | Estimated Hours | Start Date | End Date
Sprint 1 | User Story 1: As a customer, I want a dashboard page that loads when I open the app so I can easily see a summary of activity. | Task 1: Set up the initial iOS project so the team can begin development. | Bronsen Lasala | Done | 2 | 2
Sprint 1 | User Story 1: As a customer, I want a dashboard page that loads when I open the app so I can easily see a summary of activity. | Task 2: Create a landing/dashboard page that loads when the app opens. | Bronsen Lasala | Done | 3 | 4
Sprint 1 | User Story 2: As a customer, I want to be able to navigate easily between features (camera, dashboard, etc.). | Task 1: Create a navigation structure for different pages so users can easily move between features. | Merrick Fort | Done | 3 | 3
Sprint 1 | User Story 2: As a customer, I want to be able to navigate easily between features (camera, dashboard, etc.). | Task 2: Create placeholder pages for the camera, receipt, and statistics features with basic outlines of each feature. | Merrick Fort | Done | 2 | 2
Sprint 1 | User Story 3: As a customer, I want have a user profile I can log in and out of to have personalized data | Task 2: Design a database schema for users and receipts so data is organized and scalable. | Michael Tong | Done | 3 | 3
Sprint 1 | User Story 3:As a customer, I want have a user profile I can log in and out of to have personalized data | Task 3: Create API routes for authentication (login, logout, register). | Nate Bagchee | Done | 5 | 5
Sprint 1 | User Story 3: As a customer, I want have a user profile I can log in and out of to have personalized data | Task 4: Connect database with backend for login/logout flow. | Michael Tong | Done | 3 | 2

## Burnup Chart
Scrum meetings | Work Completed | Total Scope
Day 1 | 0 | 21
Day 2 | 2 | 21
Day 3 | 5 | 21
Day 4 | 8 | 21
Day 5 | 13 | 21
Day 6 | 21 | 21