## Scrum Board
Sprint | User Story | Task | Assignee | Status | Story Points | Estimated Hours | Start Date | End Date
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 1: Camera should open on moving to camera feature page. | Merrick Fort | Done | 2 | 2
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 2: Should show live camera feed prior to capturing photo | Merrick Fort | Done | 1 | 2
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 3: Should have a centering + symbol | Merrick Fort | Done | 1 | 1
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 4: Should remind user to use a dark background before taking photo | Merrick Fort | Done | 1 | 1
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 5: After a photo is taken, can crop the image to fit receipt size | Nate Bagchee | Done | 2 | 3
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 6: After a photo is cropped (or not), a confirmation is prompted to the user asking to confirm upload | Nate Bagchee | Done | 2 | 2
Sprint 2 | User Story 1: As a customer, I want to use my phone’s camera to submit a photo of any receipt so I can use them in the app | Task 7: Once confirmed, the photo should be uploaded to firebase | Nate Bagchee | Done | 2 | 2
Sprint 2 | User Story 2: As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 1: Allow users to create custom folders to organize receipts | Michael Tong | In Progress | 4 | 4
Sprint 2 | User Story 2: As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 2: Allow users to delete folders | Michael Tong | Done | 2 | 1
Sprint 2 | User Story 2: As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 3: Link image storage to cloud firestore to retrieve image urls. | Bronsen Lasala | Done | 3 | 3
Sprint 2 | User Story 2: As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 4: Cache image urls to display receipt photos in a folder | Bronsen Lasala | In Progress | 2 | 3
Sprint 2 | User Story 2: As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 5: Retrieve all the relevant receipt data from cloud firestore when a user clicks on a specific receipt (mostly placeholders for now since we haven’t extracted any data yet) | Bronsen Lasala | In Progress | 1 | 1

## Burnup Chart
Scrum meetings | Work Completed | Total Scope
2025-10-22 | 4 | 23
2025-10-24 | 9 | 23
2025-10-27 | 11 | 23
2025-10-29 | 16 | 23
2025-10-31 | 16 | 23
2025-11-03 | 16 | 23