## Scrum Board
Sprint | User Story | Task | Assignee | Status | Story Points | Estimated Hours | Start Date | End Date
Sprint 3 | User Story 1: As a customer, I want the app to scan my receipt image and extract key information like store name, total, and date so I can easily track my information [11 points] | Task 1: Define a data model for OCR-like fields and types (of data). [1] | Nate Bagchee | Done | 1
Sprint 3 | User Story 1: As a customer, I want the app to scan my receipt image and extract key information like store name, total, and date so I can easily track my information [11 points] | Task 2: Integrate on-device text recognition (VisionKit or VNRecognizrTextRequest)[3] | Nate Bagchee | Done | 3
Sprint 3 | User Story 1: As a customer, I want the app to scan my receipt image and extract key information like store name, total, and date so I can easily track my information [11 points] | Task 3: Build parsing rules like pulling store name, date, subtotal, item names, and price[3] | Nate Bagchee | Done | 3
Sprint 3 | User Story 1: As a customer, I want the app to scan my receipt image and extract key information like store name, total, and date so I can easily track my information [11 points] | Task 4: Implement a button for rescanning if extrapolation didn’t quite work as intended[1] | Bronsen Lasala | Done | 1
Sprint 3 | User Story 1: As a customer, I want the app to scan my receipt image and extract key information like store name, total, and date so I can easily track my information [11 points] | Task 6: Upload stored information to the Firebase database attached to the receipt and user [3] | Bronsen Lasala | Done | 3
Sprint 3 | User Story 2: As a customer, I want to edit the extracted receipt details so I can correct any scanning errors. [10 points] | Task 1: Build an “Edit Receipt” Screen that is prefilled from extracted text before uploading online [3 Points] | Merrick Fort | Done | 3
Sprint 3 | User Story 2: As a customer, I want to edit the extracted receipt details so I can correct any scanning errors. [10 points] | Task 2: Be able to edit receipt data that is already uploaded online, and see changes reflected in the database [3 Points] | Merrick Fort | Done | 3
Sprint 3 | User Story 2: As a customer, I want to edit the extracted receipt details so I can correct any scanning errors. [10 points] | Task 3: Track metadata (last edit) and log the information tied to the user’s profile [2 Points] | Merrick Fort | Done | 2
Sprint 3 | User Story 3: As a customer, I want to be able to take multiple photos for a single receipt, so I can scan longer receipts. | Task 1: Button for multiple photos, or default multiple photos and just choose when to scan image. [2 points] | Michael Tong | Done | 2
Sprint 3 | User Story 3: As a customer, I want to be able to take multiple photos for a single receipt, so I can scan longer receipts. | Task 2: Expand library upload to choose multiple photos from the library [2 points] | Michael Tong | In Progress | 2
Sprint 3 | User Story 3: As a customer, I want to be able to take multiple photos for a single receipt, so I can scan longer receipts. | Task 3: Data from each receipt congregated into one OCR result [1 point] | Michael Tong | Done | 2
Sprint 2 | As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 2: Cache image urls to display receipt photos in a folder [2 points] | Bronsen Lasala | Done | 2
Sprint 2 | As a customer, I want to see all the receipts I have uploaded so I can verify my past physical receipts | Task 3: Retrieve all the relevant receipt data from cloud firestore when a user clicks on a specific receipt (mostly placeholders for now since we haven’t extracted any data yet) [1 point] | Bronsen Lasala | Done | 1
28

## Burnup Chart
Scrum meetings | Work Completed | Total Scope
2025-11-05 | 2 | 28
2025-11-07 | 2 | 28
2025-11-10 | 6 | 28
2025-11-12 | 14 | 28
2025-11-14 | 20 | 28
2025-11-17 | 26 | 28