## Scrum Board
Sprint | User Story | Task | Assignee | Status | Story Points | Estimated Hours | Start Date | End Date
Sprint 4 | Sprint 3, User story 3: As a customer, I want to be able to take multiple photos for a single receipt, so I can scan longer receipts. | Task 2: Expand library upload to choose multiple photos from the library | Michael Tong | Done | 3 | 2
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 1: Add a window to the statistics page to sum the total of the last months purchases | Merrick Fort | Done | 1 | 2
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 2: Add custom filtering based on store type/category and date range | Merrick Fort | Done | 2 | 2
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 3: Add functionality to read from the data base and filter receipts by date and other information to fetch for statistics to calculate on run time | Merrick Fort | Done | 3 | 1
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 4: Cache statistics so they don’t need to be fetched when switching between pages | Bronsen Lasala | Done | 3 | 1
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 5: Add a date-range filter component that displays (This month, Last 3 Months, This Year, All-time | Bronsen Lasala | Done | 2 | 3
Sprint 4 | User Story 1: As a customer, I want to see spending statistics so that I can see my spending habits | Task 6: Add store filter component (or Any) and see receipt data from that/all stores with the provided date-range | Michael Tong | Done | 2 | 2
Sprint 4 | User Story 2: I want my receipt scans to categorize items and genres, so I can save myself time from organizing myself | Task 1: Build a dataset (as a TSV) that has instances labeled for model training | Nate Bagchee | Done | 1 | 1
Sprint 4 | User Story 2: I want my receipt scans to categorize items and genres, so I can save myself time from organizing myself | Task 2: Train multiple ML models in Python (Logistic regression) on OCR extracted receipts, selecting the model with optimal accuracy | Nate Bagchee | Done | 1 | 1
Sprint 4 | User Story 2: I want my receipt scans to categorize items and genres, so I can save myself time from organizing myself | Task 3: Deploy the trained model into the project and connect it to our classification of data on a receipt | Nate Bagchee | Done | 3 | 3

## Burnup Chart
Scrum meetings | Work Completed | Total Scope
2025-11-19 | 0 | 21
2025-11-21 | 0 | 21
2025-11-24 | 6 | 21
2025-11-26 | 9 | 21
2025-11-28 | 12 | 21
2025-12-02 | 21 | 21